## Revised Schedule
Task Name | Start | End | Duration (days)
System Architecture & Design | 2017-03-31 | 2017-04-02 | 2
UI Implementation | 2017-04-02 | 2017-04-09 | 7
Implement A.I. Logic | 2017-04-09 | 2017-04-21 | 12
Evaluation Testing | 2017-04-14 | 2017-04-28 | 14
Evaluation Review and Documentation | 2017-04-28 | 2017-05-12 | 14
Final Implementation | 2017-05-12 | 2017-05-15 | 3
Important Project Dates
Date | Milestone
2017-02-17 | Report 1: Feasibility Study
2017-03-17 | Assignment 2: Presentation 1
2017-03-17 | Report 2
2017-04-14 | Assignment 3: Presentation 2
2017-04-14 | Report 3
2017-05-10 | Assignment 4: Presentation and Demonstration
2017-05-18 | Project Delivery (report, code, documentation)

## Original Schedule
Task Name | Start | End | Duration (days)
System Architecture & Design I | 2017-02-18 | 2017-03-03 | 13
System Architecture & Design II | 2017-03-04 | 2017-03-10 | 6
Organizer UI Implementation | 2017-03-11 | 2017-03-24 | 13
Competitor UI Implementation | 2017-03-25 | 2017-03-31 | 6
Server and Database Implementation | 2017-04-01 | 2017-04-14 | 13
Integration, UI Feedback, and Testing | 2017-04-15 | 2017-04-28 | 13
Final Implementation | 2017-04-29 | 2017-05-08 | 9
0
0
0
0
0